## Sheet1
Phase | Timeline | Key Milestones
1. Set Up the BI Platform and Data Warehouse | Months 1–2 | Finalize vendor contracts, configure cloud infrastructure, and build centralized data storage.
2. Connect Data Sources Through ETL Integration | Months 3–4 | Map, clean, and integrate ad performance, seller, and customer data using ETL pipelines.
3. Develop Seller-Facing Dashboards and Predictive Tools | Months 5–6 | Design dashboards, set up predictive analytics, and integrate A/B testing features.
4. Train Internal Teams and Sellers | Months 7–8 | Conduct training for Etsy teams; create onboarding guides, tutorials, and support resources for sellers.
5. Establish Security and Governance Protocols | Months 7–8 (parallel) | Implement data protection, compliance standards, and transparency measures alongside training.
6. Launch, Monitor, and Iterate | Months 9–10 | Run pilot launch, gather feedback, roll out in phases, monitor adoption, and refine based on seller input.

## Sheet2
Category | Requirement | Quantity | Estimated Cost
Data Collection | Real-time streaming tools (Kafka, etc.) | 1 system setup | 140000
| External data API integrations | 3–5 APIs | 50000
| Data Engineers | 2 FTEs | $240,000/year
Data Management | Cloud Data Warehouse (Snowflake, BigQuery) | 1 subscription | $280,000/year
| Data Governance Tools | 1 license | $90,000/year
| Cloud Infrastructure (AWS, GCP) | Usage-based | $160,000/year
Data Mining/AI | Predictive Analytics Platform (Databricks, etc.) | 1 license | $230,000/year
| Data Scientists | 2 FTEs | $280,000/year
| ML Engineer | 1 FTE | $140,000/year
Analytics & Reporting | BI Tool License (Looker, Tableau) | 1 license | $200,000/year
| Seller Dashboard Customization | Initial build | 70000
| Seller and Staff Training Programs | 4 workshops | 40000
Monitoring | Automated Reporting & Alerts | 1 setup | 50000
| KPI Standardization Project | 1 internal initiative | 30000
| Support & Monitoring Staff | 1–2 FTEs | $160,000/year
Compliance & Security | Data Privacy Compliance (GDPR, CCPA) Audits | 2 audits | 40000
| Security Tools and Encryption | 1 implementation | 100000
Change Management | Change Management Lead | 1 FTE | $120,000/year
| Communication & Rollout Campaign | Organization-wide | 50000
Total Estimated First-Year Cost |  |  | ~$3.1 million

## ROI
Category | Amount (USD) | Description
Annual Benefit | 4700000 | Total estimated annual benefits from the BI solution
Total Investment (3 Years) | 3180000 | Total cost of investment over three years
Net Profit | 1520000 | $4,700,000 – $3,180,000
ROI (Annual) | 47.8% | ($1,520,000 ÷ $3,180,000) × 100
Raw 3-Year ROI | 143.4% | 47.8% × 3 (without adjusting for time value or ramp-up)
Adjusted 3-Year ROI | ~84% | More realistic estimate accounting for phase-in and ramp-up